## Sheet1
| Version 1 |  | Version 2 |  | Version 3 |  | Comments
| Original Plan | Delivered On | Original Plan | Delivered On | Original Plan | Delivered On
1. GUI Development
1.1 Patient Menu | October 30th, 2017 | November 2th, 2017 |  |  |  |  | Completed to schedule
1.2 Settings Menu | October 30th, 2018 | November 2th, 2018 |  |  |  |  | Completed to schedule
1.3 Safe Zones Menu | November 5th, 2017 | November 6th, 2017 |  |  |  |  | Completed to schedule
1.4 Analytics Menu | November 5th, 2017 | November 6th, 2017 |  |  |  |  | Completed to schedule
1.5 Caretaker Menu | November 5th, 2017 | November 6th, 2017 |  |  |  |  | Completed to schedule
2. Core Location Features
2.1 Patient Location Tracking | November 5th, 2017 | November 6th, 2017 |  |  |  |  | Completed to schedule
2.2 Safe Zone Creation |  |  | November 10th, 2017 | November 6th, 2017 |  |  | Completed to schedule
2.3 Safe Zone Editing |  |  | November 10th, 2017 | November 6th, 2017 |  |  | Completed to schedule
2.4 Bookmark Creation | November 4th, 2017 | November 6th, 2017 |  |  |  |  | Completed to schedule
2.5 Bookmark Editing | November 4th, 2017 | November 6th, 2017 |  |  |  |  | Completed to schedule
2.6 Bookmark Navigation |  |  | November 19th, 2017 | November 19th, 2017 |  |  | Completed to schedule
2.7 Take Me Home Button | November 5th, 2017 | November 6th, 2017 |  |  |  |  | Completed to schedule
2.8 Location History |  |  | November 10th, 2017 | November 19th, 2017 |  |  | Completed to schedule
2.9 Basic Navigation |  |  | November 17th, 2017 | November 19th, 2017 |  |  | Completed to schedule
2.10 AR Navigation |  |  |  |  | November 29th, 2017 | November 28th, 2017 | Completed to schedule
2.11 Safe Zone Alerts |  |  |  |  | November 25th, 2017 | Dec 1th, 2017 | Completed to schedule
2.12 Turn-by-turn Navigation |  |  |  |  | November 25th, 2017 | Dec 1th, 2017 | Completed to schedule
3. UI Refinement and Extras
3.1 UI Colour and Sizing |  |  |  |  | December 2nd 2017 | December 2nd 2017 | Completed to schedule
3.2 Video Tutorials |  |  |  |  | December 3rd 2017 | December 3rd 2017 | Completed to schedule